## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | The rest of user stories related to projects using react | 2 | Mahmoud Ahmed | Mohamed Aboelazaiem | Seif elkholy
1.1 | The rest of user stories related to projects using react | 2 | Mohamed Aboelazaiem | Mahmoud Ahmed | Youssef Hassan
1.2 | The rest of cruds related to Partner using react | 2 | Seif elkholy | Mahmoud Ahmed | Mahmoud Selim
1.3 | The rest of cruds related to Locations using react. | 5 | Youssef el shihy | Youssef Hassan | Mohamed Galal
1.4 | The rest of cruds related to Candidate using react. | 5 | Mahmoud Nabil | Youssef el shihy | Mohamed Saher
1.5 | The rest of cruds related to Consulting-Agent using react. | 5 | Youssef Hassan | Seif elkholy | Mahmoud Nabil
1.6 | The rest of cruds related to Admin using react. | 5 | Mahmoud Selim | Mahmoud Nabil | Amr AbdelNabi
1.7 | The rest of cruds related to Admin using react. | 5 | Mohamed Saher | Youssef Shihy | Mahmoud Selim
1.8 | The rest of cruds related to Co-Working space . | 5 | Amr AbdelNabi | Mahmoud Nabil | Youssef el shihy
1.9 | The rest of cruds related to Co-Working space . | 5 | Moahmed Galal | Amr abd elNabi | Youssef Hassan
2 | Implementing nodemailer for email notifications backend and frontend | 6 | Mohamed Aboelazaiem
2.1 | Refactoring the backend user stories from scratch. | Undefined | Mahmoud Ahmed
2.2 | Free Text-Search in the backend . | Undefined | Seif elkholy