## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | implement User Model in MongoDB | 3 | Mohamed Aboelazaiem | Mahmoud Ahmed | Mahmoud Nabil
1.1 | implement Project Model in MongooDB | 3 | Mahmoud Ahmed | Mohamed Aboelazaiem | Mahmoud Nabil
1.2 | implement Location Model in MongooDB | 3 | Youssef El-shihy | Youssef Hassan | Seif Elkholy
1.3 | CRUD For Member that suport MongooDB | 3 | Mahmoud Nabil | Youssef El-Shihy | Mahmoud Selim
1.4 | CRUD For Partner that supports MongooDB | 3 | Seif ElKholy | Mahmoud Nabil | Youssef Hassan
1.5 | CRUD For Consultancy Agency that supports MongooDB | 3 | Youssef Hassan | Seif El-Kholy | Youssef el Shihy
1.6 | Create & Review For Co-Working Space that supports MongooDB | 3 | Amr Abdelnabi | Mahmoud Ahmed | Mohamed Aboelazaiem
1.7 | Update & Delete For Co-Working Space that supports MongooDB | 3 | Mohamed Galal | Mahmoud Ahmed | Mohamed Aboelazaiem
1.8 | CRUD For Admin that supports MongooDB | 3 | Mohamed Saher | Mahmoud Ahmed | Mohamed Aboelazaiem
1.9 | CRUD For Project that supports MongooD | 3 | Mahmoud Ahmed | Mohamed Aboelazaiem | Mahmoud Nabil
1.11 | CRUD For Location that supports MongooDB |  | Youssef El-Shihy | Mahmoud Nabil | Mahmoud Selim
2 | As a Partner I want to submit a descreption of a Project so that I can find someone to do it | 3 | Mahmoud Ahmed | Mohamed Aboelazaiem | Mahmoud Nabil
2.1 | As an Admin I want to view projects that havent been approved yet so I can decide to approve or dissaprove | 3 | Mahmoud Ahmed | Mohamed Aboelazaiem | Mahmoud Nabil
2.2 | As an Admin I want to see members that applied to a project so I can choose them or not | 3 | Mahmoud Ahmed | Mohamed Aboelazaiem | Mahmoud Nabil
2.3 | As an Admin I want to assign a candidate member to a project so that he can work on it | 3 | Mahmoud Ahmed | Mohamed Aboelazaiem | Mahmoud Nabil
2.4 | As a member I want to apply for a project so that I can work on the projects if I am accepted | 3 | Mahmoud Ahmed | Mohamed Aboelazaiem | Mahmoud Nabil