## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As an Admin I want to approve/dissaprove projects to be published so candidates can see them | 3 | Mahmoud Ahmed | Mohamed Aboelazaiem | Seif elkholy
1.1 | As a Member I want to apply to a Project that im certified for so I can work on it | 5 | Mahmoud Ahmed | Mohamed Aboelazaiem | Seif elkholy
1.2 | As a User I want to see a locations calenders so I can reserve a location if I want to & creating calender for location | 7 | Youssef el shihy | Mahmoud Ahmed | Mohamed Aboelazaiem
1.3 | As a User I want to be able to request a reservation | 3 | Youssef el shihy | Mahmoud Ahmed | Mohamed Aboelazaiem
1.4 | As a Co-Working space I should be able to see reservation requests so I can confirm or not | 3 | Youssef el shihy | Mahmoud Ahmed | Mohamed Aboelazaiem
1.5 | As a Co-Working space I should be able to confirm or decline a reservation request and reflect on calender | 5 | Youssef el shihy | Mahmoud Ahmed | Mohamed Aboelazaiem
1.6 | Jtests for Project entity | 2 | Mahmoud Ahmed | Mohamed Aboelazaiem | Seif elkholy
1.7 | Jtests for Location entity | 2 | Youssef el shihy | Mahmoud Ahmed | Mohamed Aboelazaiem
1.8 | Jtests for Members entity | 2 | Mahmoud Nabil | Mahmoud Selim | Amr Abd el Nabi
1.9 | Jtests for Partner Entity | 2 | Seif elkholy | Mohamed Aboelazaiem | Mahmoud Nabil
2 | Jtests for admin | 2 | Mahmoud Selim/Mohamed Saher | Mohamed Galal | Mahmoud Nabil
2.1 | Jtests for Co-working space | 2 | Amr Abd el nabi/Mohamed Galal | Youssef Hassan | Seif elkholy
2.2 | Jtests for consultancy Agency | 2 | Youssef Hassan | Mohamed Saher | Mahmoud Selim
2.3 | As a User I want to receive a notification so I can know if my reservation requesnt has been confirmed or not | 6 | Mohamed Aboelazaiem | Mahmoud Ahmed | youssef el shihy
2.4 | As A Partner I should be notified if a Member got accpeted to work on I project so I can send him an invite | 6 | Mohamed Aboelazaiem | Mahmoud Ahmed | Youssef el shihy
2.5 | Researching about free text search that should be implemented in later sprint |  | Seif elkholy
| Researching about Recomender System Algorithms using tensor.js or k-tree nearest neighbor algorithms |  | Mahmoud Ahmed