## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Entity candidate:Create | 3 | Mahmoud Nabil
1.1 | Entity candidate:Review | 2 | Mahmoud Nabil
1.2 | Entity candidate:Update | 3 | Mahmoud Nabil
1.3 | Entity Candidate:Delete | 2 | Mahmoud Nabil
2 | Entity Partner:Create | 3 | Seif ElKholy
2.1 | Entity Partner:Review | 2 | Seif ElKholy
2.2 | Entity Partner:update | 3 | Seif ElKholy
2.3 | Entity Partner:Delete | 2 | Seif ElKholy
3 | Entity Consultancy Agency:Create | 3 | Youssef Hassan
3.1 | Entity Consultancy Agency:Review | 2 | Youssef Hassan
3.2 | Entity Consultancy Agency:Update | 3 | Youssef Hassan
3.3 | Entity Consultancy Agency:Delete | 2 | Youssef Hassan
4 | Entity Co-working Space:Create | 3 | Amr abdelnabi | depends on 4.2/4.3 | As a co-working space
4.1 | Entity Co-working Space:Review | 2 | Amr abdelnabi |  | I should be able to sign up
4.2 | Entity Co-working Space:Update | 3 | mohamed Jalal | depends on 4.0/4.1 | andupdate and be viewed
4.3 | Entity Co-working Space:Delete | 2 | mohamed Jalal |  | and deleted
5 | Entity Admin:Create | 3 | Mahmoud Selim | depends on 5.2/5.3 | As an Admin I should be
5.1 | Entity Admin:Review | 2 | Mahmoud Selim |  | able to sign up and
5.2 | Entity Admin:Update | 3 | mohamed saher | depends on 5.0/5.1 | update and be viewed
5.3 | Entity Admin:Delete | 2 | mohamed saher |  | and deleted
6 | Entity Project:Create | 3 | Mahmoud Ahmed
6.1 | Entity Project:Review | 2 | Mahmoud Ahmed
6.2 | Entity Project:Update | 3 | Mahmoud Ahmed
6.3 | Entity Project:Delete | 2 | Mahmoud Ahmed
7 | Entity Location:Create | 3 | Youssef El-shihy
7.1 | Entity Location:Review | 2 | Youssef El-shihy
7.2 | Entity Location:Update | 3 | Youssef El-shihy
7.3 | Entity Location:Delete | 2 | Youssef El-shihy
8 | Entity Notification:Create | 3 | Mohamed Aboelazaiem
8.1 | Entity Notification:Review | 2 | Mohamed Aboelazaiem
8.2 | Entity Notification:Update | 3 | Mohamed Aboelazaiem
8.3 | Entity Notification:Delete | 2 | Mohamed Aboelazaiem
9 | Message enitity (CRUD) | 10 | Mohamed Aboelazaiem